## Worksheet
Operations Dashboard - Gantt Chart (One Page)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
T001 | Project Initiation | 2024-04-01 | 2024-04-15 | 15 | Completed
T002 | Requirements Gathering | 2024-04-16 | 2024-05-15 | 30 | In Progress
T003 | Design Phase | 2024-05-16 | 2024-06-30 | 45 | In Progress
T004 | Development Sprint 1 | 2024-07-01 | 2024-07-31 | 31 | Delayed
T005 | Testing & QA | 2024-08-01 | 2024-09-30 | 61 | Completed
T006 | User Training | 2024-10-01 | 2024-10-15 | 15 | Completed
T007 | Go-Live & Deployment | 2024-10-16 | 2024-10-31 | 16 | In Progress
Total Duration: |  |  |  | 208 Days | Overall Progress: 67%