## Worksheet
Operations Dashboard - Planning View (Gantt Chart)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress
T001 | Project Initiation | 2025-04-01 | 2025-04-05 | 5 | In Progress
T002 | Requirements Gathering | 2025-04-06 | 2025-04-15 | 10 | In Progress
T003 | Design Phase | 2025-04-16 | 2025-04-30 | 15 | Pending
T004 | Development Sprint 1 | 2025-05-01 | 2025-05-14 | 14 | Pending
T005 | Development Sprint 2 | 2025-05-15 | 2025-06-14 | 31 | Pending
T006 | Testing & QA | 2025-06-15 | 2025-07-14 | 31 | Pending
T007 | Deployment Preparation | 2025-07-15 | 2025-07-31 | 17 | Pending
T008 | Go-Live | 2025-08-01 | 2025-08-01 | 1 | Milestone (Critical)
T009 | Project Closure | 2025-08-15 | 2025-08-31 | 17 | Milestone (Critical)
T010 | Post-Implementation Review | 2025-09-01 | 2025-09-31 | 31 | Critical Path Delayed
T011 | Documentation Finalization | 2025-09-05 | 2025-09-31 | 27 | Pending