## Worksheet
Operations Dashboard
Gantt Chart - Project Timeline & Progress Tracking
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress
001 | Requirements Gathering | John Doe | 2023-10-01 | 2023-10-15 | Completed | 100%
002 | System Design & Architecture | Jane Smith | 2023-10-16 | 2023-11-05 | Completed | 100%
003 | Frontend Development | Alex Johnson | 2023-11-06 | 2024-01-15 | Ongoing | 65%
004 | Backend Development | Emma Brown | 2023-11-06 | 2024-01-31 | Ongoing | 58%
005 | Testing & QA | Chris Lee | 2024-01-16 | 2024-03-15 | Delayed | 35%
006 | User Training & Documentation | Lisa Wong | 2024-03-16 | 2024-04-15 | Not Started | 0%
007 | Deployment & Go-Live | Mark Taylor | 2024-04-16 | 2024-05-31 | Not Started | 0%