## Worksheet
Operations Dashboard - Gantt Chart
Small Business Version ¦ Updated: October 2023
Task Name | Start Date | End Date | Duration (Days) | Status | Progress
Project Planning | 2023-10-01 | 2023-10-07 | 7 | Completed
Market Research | 2023-10-08 | 2023-10-15 | 8 | Completed
Product Design | 2023-10-16 | 2023-10-31 | 16 | Completed
Prototype Development | 2023-11-01 | 2023-11-15 | 15 | In Progress
User Testing | 2023-11-16 | 2023-11-30 | 15 | Pending
Final Adjustments | 2023-12-01 | 2023-12-15 | 15 | Pending
Launch Preparation | 2023-12-16 | 2023-12-31 | 16 | Pending
Go Live | 2024-01-01 | 2024-01-31 | 31 | Pending
Post-Launch Review | 2024-02-01 | 2024-02-15 | 15 | Pending
Reporting & Analysis | 2024-02-16 | 2024-03-15 | 30 | Pending
Total Project Duration: |  |  | 148 days