## Worksheet
Operations Dashboard - Tracking View
Task ID | Task Name | Owner | Status | Start Date | Due Date | Timeline (2024)
T001 | System Upgrade Planning | John Smith | In Progress | 2024-01-15 | 2024-03-31
T002 | Database Migration | Alice Johnson | In Progress | 2024-03-15 | 2024-06-30
T003 | User Training Sessions | Michael Brown | Delayed | 2024-05-15 | 2024-07-31
T004 | Final System Testing | Sarah Wilson | Completed | 2024-07-15 | 2024-08-31
T005 | Go-Live Deployment | Robert Davis | In Progress | 2024-08-15 | 2024-09-30