## Worksheet
Weekly Maintenance Log
Operations Dashboard - Weekly Summary Report
Reporting Period:Monday, June 10, 2024 – Sunday, June 16, 2024
Prepared By:Operations Team ¦Date:June 17, 2024
# | Maintenance Task | Location/Area | Planned Date | Actual Date Completed | Status | Responsible Team/Personnel | Notes/Comments
1 | HVAC System Inspection & Filter Replacement | Main Building - Level 2 | Mon, Jun 10 | Tue, Jun 11 | Completed | Facilities Team - John D. | Filters replaced; system running efficiently.
2 | Pump Maintenance (Water Supply System) | Mechanical Room - Sub-Level 1 | Tue, Jun 11 | Tue, Jun 11 | Completed | Engineering - Sarah M. | Oil level checked; no leaks detected.
3 | Lift Safety Inspection & Certification Update | Parking Garage - Elevator A | Wed, Jun 12 | Wed, Jun 12 | Completed | Compliance Department - Mark T. | Certification renewed; report submitted.
4 | Fire Alarm System Test & Calibration | All Floors, Main Building | Thu, Jun 13 | Thu, Jun 13 | Completed | Safety Team - Linda R. | All zones tested successfully.
5 | Generator Load Test (Monthly) | Backup Power Room | Fri, Jun 14 | Fri, Jun 14 | Completed | Electrical Team - Tom K. | Full load test passed; battery levels optimal.
6 | Flooring Repair (Cafeteria Area) | Cafeteria - West Wing | Sat, Jun 15 | Not Started | Pending | Contractor - ABC Maintenance Inc. | Waiting on material delivery. Scheduled for Mon, Jun 17.
7 | Cleaning & Sanitization of HVAC Ducts (High-Priority) | Server Room - Level 3 | Sun, Jun 16 | Not Started | In Progress | Specialized Cleaning Crew - Alex P. | Work in progress; expected completion by end of day.