## Worksheet
Operations Dashboard - Monthly Planner (Data Version)
Month: October 2024
Task ID | Department | Task Description | Planned Start Date | Planned End Date | Status | Progress (%)
TASK-001 | Production | Monthly Machine Calibration & Maintenance | 2024-10-02 | 2024-10-05 | Completed | 100%
TASK-002 | Quality Control | Final Product Inspection Batch #4567 | 2024-10-03 | 2024-10-15 | Pending | 65%
TASK-003 | Supply Chain | Supplier Contract Review & Negotiation Q4 | 2024-10-01 | 2024-10-31 | Pending | 35%
TASK-004 | HR & Admin | Employee Onboarding Sessions - Q4 Cohort | 2024-10-10 | 2024-10-31 | Pending | 45%
TASK-005 | IT Support | System Backup & Security Audit | 2024-10-18 | 2024-10-25 | Delayed | 30%
TASK-006 | Marketing | Q4 Campaign Launch Preparation | 2024-10-21 | 2024-11-30 | Pending | 15%
TASK-007 | Finance | Monthly Financial Reporting & Forecasting | 2024-10-28 | 2024-11-15 | Pending | 5%