## Worksheet
Operations Dashboard - Monthly Planner (Manager View)
Project / Task | Owner | Key Metrics (Monthly) |  |  |  |  | Status | Priority
|  | Target Completion | Actual Completion | Progress (%) | Budget (USD) | Deviation (%)
Q3 Product Launch | Jane Doe | 2024-09-15 | 2024-09-14 | 98% | $185,000 | -3.5% | Completed | High
HR Onboarding System Upgrade | Mike Smith | 2024-09-20 | 2024-09-18 | 95% | $68,500 | -1.2% | Completed | Medium
Supply Chain Optimization | Sarah Lee | 2024-09-30 | 2024-09-16 | 75% | $135,700 | +5.8% | Ongoing | High
Customer Feedback Portal Revamp | Tom Brown | 2024-09-25 | - | 45% | $89,300 | +13.6% | Delayed | Medium
IT Infrastructure Audit | Lisa Wang | 2024-09-10 | 2024-09-13 | 98% | $55,600 | -7.3% | Completed | Low
Total | - | - | - | 78% | $534,100 | +0.9% | - | -