## Worksheet
Operations Dashboard - Monthly Planner (April 2024)
Task | Owner | Planned Start | Planned End | Status | Weekly Progress (Apr 1 - Apr 30)
[5 empty] | Week 1 (Apr 1-7) | Week 2 (Apr 8-14) | Week 3 (Apr 15-21) | Week 4 (Apr 22-30) | Total | Budget | Remarks
Project Initialization
Define project scope & goals | John Smith | Apr 1, 2024 | Apr 5, 2024 | Completed | 100% | - | - | - | 100% | $2,500 | On schedule.
Team Planning & Allocation
Assign team roles and responsibilities | Jane Doe | Apr 3, 2024 | Apr 7, 2024 | Completed | 100% | - | - | - | 100% | $3,200 | Team alignment achieved.
Execution Phase
Develop core workflow system | Mike Johnson | Apr 10, 2024 | Apr 25, 2024 | In Progress | 30% | 55% | 80% | - | 80% | $12,400 | Slight delay in API integration.
Monitoring & Evaluation
Weekly performance review meetings | Sarah Wilson | Every Monday | Apr 30, 2024 | In Progress | Meeting held weekly; feedback integrated.
Total Monthly Goals: | [5 empty] | 100% | 105% | 80% | - | 94% | $23,650 | N/A
Monthly Summary & Forecast (April 2024)
Overall Performance: The team achieved 94% of planned deliverables. Two tasks are ahead of schedule, one is on track, and one minor delay occurred due to integration challenges. Budget utilization remains under control at 97% of allocated amount.
Next Month Focus: Complete workflow development, initiate user testing phase, finalize documentation. Target completion rate of 95%.