## Worksheet
Operations Dashboard - Monthly Planner
Project/Task | Owner | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | % Complete
Q4 Marketing Campaign | Jane Smith | 2023-10-05 | 2023-11-30 | 2023-10-15 | - | In Progress | 75%
System Upgrade v2.0 | Mike Johnson | 2023-10-10 | 2023-11-15 | - | - | Delayed | 0%
HR Onboarding Process Revamp | Sarah Lee | 2023-10-18 | 2023-11-30 | 2023-10-18 | 2023-11-5 | Completed | 100%
New Product Launch Prep | David Chen | 2023-11-01 | 2023-11-30 | - | - | In Progress | 45%
Customer Feedback Analysis | Lisa Wong | 2023-10-01 | 2023-10-31 | 2023-10-5 | 2023-10-31 | Completed | 100%
Total Tasks: 5 ¦ Completed: 2 ¦ In Progress: 2 ¦ Delayed: 1 | [5 empty] | Avg. Completion Rate: 60%