## Monthly Operations Dashboard
Monthly Operations Dashboard
Planner Template - Monthly Overview
Task/Activity | Responsible Team | Due Date | Status | Priority | Budget Allocated (USD) | Actual Spend (USD)
Monthly Production Planning | Operations Team | 2024-04-05 | In Progress | High | $15,000.00 | $13,756.89
Supply Chain Review Meeting | Procurement & Logistics | 2024-04-10 | Completed | Medium | $5,000.00 | $4,892.33
Quality Assurance Audit | QA Department | 2024-04-15 | Not Started | High | $8,500.00 | $0.00
Staff Training Session | HQ Human Resources | 2024-04-18 | In Progress | Medium | $12,000.00 | $9,754.65
Monthly KPI Report Compilation | Data Analytics Team | 2024-04-25 | Not Started | Low | $3,500.00 | $1,236.78
Monthly Summary
Total Budget Allocated:$44,000.00
Total Actual Spend:$39,641.65
Budget Variance:+$4,358.35 (Under Budget)
Completion Rate:40%