## Worksheet
Operations Dashboard - Tracking View
Task ID | Task Name | Description | Assigned To | Start Date | Due Date | Status | Prioritization Level | Action Items (Count)
OP-001 | System Upgrade Preparation | Finalize test environment setup and documentation. | Alice Johnson | 2024-04-15 | 2024-04-30 | In Progress | High Priority | 7
OP-002 | Inventory Audit Cycle | Conduct monthly physical inventory audit across all warehouse locations. | Robert Chen | 2024-04-18 | 2024-05-15 | Pending | Medium Priority | 3
OP-003 | Daily Report Generation Script Update | Optimize report generation logic for faster execution. | Lisa Park | 2024-04-10 | 2024-04-11 | Completed | Low Priority | 2
OP-004 | User Access Review Process | Conduct access review for all department staff. | Sarah Williams | 2024-03-28 | 2024-04-15 | Overdue | High Priority | 5
OP-005 | Customer Feedback Analysis Sprint | Analyze Q1 feedback and draft action plan. | Daniel Torres | 2024-04-16 | 2024-05-10 | In Progress | Medium Priority | 6
OP-006 | Supply Chain Risk Assessment | Evaluate supplier reliability and mitigation strategies. | Maria Garcia | 2024-04-17 | 2024-05-31 | Pending | High Priority | 8
OP-007 | Employee Onboarding Checklist Update | Revise onboarding process to improve new hire experience. | Jane Smith | 2024-03-15 | 2024-03-18 | Completed | Low Priority | 4
OP-008 | KPI Dashboard Enhancement | Improve visualization and interactivity for key metrics. | Tom Wilson | 2024-04-19 | 2024-05-18 | In Progress | Medium Priority | 9