## Worksheet
Operations Dashboard
Project Plan - Advanced Template
Task ID | Task Name | Owner | Start Date | Due Date | Status | % Complete | Budget Allocated ($)
Phase 1: Planning & Requirements
PRJ-001 | Stakeholder Analysis & Requirements Gathering | Jane Smith (PM) | 01 Jan 2024 | 15 Feb 2024 | Completed | 100% | 95,000
Phase 2: System Design & Architecture
PRJ-005 | Application Architecture Design | Mark Johnson (Lead Architect) | 16 Feb 2024 | 31 Mar 2024 | In Progress | 85% | 180,000
Phase 3: Development & Testing
PRJ-012 | User Interface Development (Frontend) | Anna Lee (Dev Lead) | 01 Apr 2024 | 30 Jun 2024 | In Progress | 65% | 375,000
PRJ-013 | Backend API Development & Integration | Derek Brown (Dev Lead) | 15 Apr 2024 | 15 Aug 2024 | In Progress | 70% | 390,000
Phase 4: Quality Assurance & Deployment
PRJ-018 | System Testing & Bug Fixing | Sarah Williams (QA Manager) | 01 Sep 2024 | 30 Sep 2024 | Pending Start | 5% | 150,000
Phase 5: Go-Live & Post-Implementation
PRJ-024 | Production Deployment & Cutover | Chris Miller (Ops Lead) | 01 Oct 2024 | 31 Oct 2024 | Pending Start | 0% | 85,000
Support & Optimization
PRJ-027 | Post-Implementation Review & Optimization | Linda Chen (PMO) | 01 Nov 2024 | 31 Dec 2024 | Pending Start | 0% | 75,000
Total Project Cost: | [6 empty] | $1,850,000
Generated on:¦ Version 2.1 (Advanced Template)