## Worksheet
Annual Project Plan - Operations Dashboard
Project Name | Description | Q1 (Jan-Mar) |  |  |  | Q2 (Apr-Jun) |  |  |  | Q3 (Jul-Sep) |  |  |  | Q4 (Oct-Dec)
|  | Planned Start | Actual Start | Target End | Status | Planned Start | Actual Start | Target End, Status (Progress)
[12 empty] | Planned Start | Actual Start | Target End | Status
System Integration Upgrade | Implement new core platform integration with CRM & ERP systems. | Jan 05, 2024 | - | Mar 31, 2024 | On Track | Apr 15, 2024 | - | Jun 30, 2024 - In Progress (68%) |  | Jul 15, 2024 | - | Sep 30, 2024 | On Track | Oct 15, 2024 | - | Dec 31, 2024 - On Track (85%)
Customer Portal Redesign | Modernize user interface and improve accessibility features. | Jan 10, 2024 | - | Mar 31, 2024 | Completed | Apr 15, 2024 | - | Jun 30, 2024 - In Progress (75%) |  | Jul 15, 2024 | - | Sep 30, 2024 | On Track | Oct 15, 2024 | - | Dec 31, 2024 - On Track (88%)
Supply Chain Analytics | Build real-time dashboard for logistics performance tracking. | Jan 01, 2024 | - | Mar 31, 2024 | Delayed (Revised) | May 05, 2024 | - | Jun 30, 2024 - Delayed (45%) |  | Jul 15, 2024 | - | Sep 30, 2024 | On Track (63%) | Oct 15, 2024 | - | Dec 31, 2024 - On Track (79%)
HR Digital Transformation | Rollout of new HRIS and employee self-service portal. | Feb 01, 2024 | - | Apr 30, 2024 | Completed | May 15, 2024 | - | Jul 31, 2024 - In Progress (59%) |  | Aug 15, 2024 | - | Oct 31, 2024 | On Track (76%) | Nov 01, 2024 | - | Dec 31, 2024 - On Track (95%)
Sustainability Reporting Platform | Develop ESG data collection and reporting framework. | Jan 20, 2024 | - | Mar 31, 2024 | Completed | Apr 15, 2024 | - | Jun 30, 2024 - In Progress (78%) |  | Jul 15, 2024 | - | Sep 30, 2024 | On Track (91%) | Oct 15, 2024 | - | Dec 31, 2024 - On Track (98%)
Total Projects: |  |  |  |  | 5 | - | Completed: | 2 | - | On Track: | 3 | - | Delayed: | 0 (Revised)
Overall Annual Progress: | [8 empty] | 84% - On Schedule with Minor Delays in Planning Phases