## Worksheet
Project | Phase | Start Date | End Date | Status | Owner
Website Redesign | Planning | 2023-09-01 | 2023-09-15 | In Progress | Jane Smith
Website Redesign | Design | 2023-09-16 | 2023-10-15 | In Progress | Jane Smith
Website Redesign | Development | 2023-10-16 | 2023-12-01 | Pending | Mike Johnson
Website Redesign | Testing | 2023-12-02 | 2023-12-15 | Pending | Sarah Lee
Website Redesign | Deployment | 2023-12-16 | 2023-12-31 | Pending | Mike Johnson
Mobile App Launch | Planning | 2023-08-20 | 2023-09-10 | Completed | Alex Brown
Mobile App Launch | Design | 2023-09-11 | 2023-10-05 | Completed | Alex Brown
Mobile App Launch | Development | 2023-10-06 | 2024-01-31 | In Progress | Lisa Wong
Mobile App Launch | Testing | 2024-02-01 | 2024-03-15 | Pending | Lisa Wong
Mobile App Launch | Deployment | 2024-03-16 | 2024-03-31 | Pending | Alex Brown