## Worksheet
Operations Dashboard
Project Plan - Client View
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Progress (%)
PJ001 | Project Initiation & Kickoff | Client Management Team | 2024-04-15 | 2024-04-25 | Completed | 100%
PJ002 | Requirements Gathering & Approval | Business Analysts | 2024-04-26 | 2024-05-15 | In Progress | 70%
PJ003 | Design Phase & Prototyping | UX/UI Designers | 2024-05-16 | 2024-06-15 | In Progress | 30%
PJ004 | Development & Coding | Development Team | 2024-06-16 | 2024-08-31 | Delayed | 25%
PJ005 | Testing & QA | QA Engineers | 2024-09-01 | 2024-10-15 | Completed | 100%
PJ006 | Deployment & Go-Live | DevOps Team | 2024-10-16 | 2024-11-30 | Completed | 100%
Project Summary
Total Tasks: | 6 | Completed: | 3
In Progress: | 2 | Delayed: | 1
Avg. Progress: | 50% | Overall Status: | On Track
Notes:This dashboard provides a real-time view of project progress for client stakeholders. All data is updated weekly and reflects the current status as of April 25, 2024.