## Worksheet
Operations Dashboard
Daily Project Plan - Status Update as of 2024-04-05
Project ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
PJ001 | Website Redesign Phase 1 - UI Mockups | Jane Smith | 2024-03-25 | 2024-04-05 | Delayed | 75%
PJ002 | Backend API Development - User Module | Mike Johnson | 2024-03-30 | 2024-04-15 | On Track | 68%
PJ003 | Database Migration - Legacy System to Cloud | Sarah Lee | 2024-04-01 | 2024-04-10 | On Track | 95%
PJ004 | QA Testing - Integration Scenarios | David Brown | 2024-04-03 | 2024-04-15 | On Track | 35%
PJ005 | Client Onboarding & Training Sessions | Lisa Wong | 2024-04-05 | 2024-04-18 | Pending Start | 0%
PJ006 | Marketing Campaign Launch Preparation | Tom Reed | 2024-03-31 | 2024-04-12 | On Track | 85%
Today's Focus:Complete UI mockups (PJ001), initiate QA testing for integration scenarios (PJ004).