## Worksheet
Operations Dashboard - Project Plan
Detailed Project Plan & Performance Tracking ¦ Updated: October 26, 2023
Project ID | Project Name | Initiator | Department | Status | Start Date | End Date | Budget (USD) | Actual Cost (USD) | % Complete | Risk Level | Next Milestone
PJ001 | Enterprise CRM Upgrade | Sarah Johnson | IT & Operations | In Progress | 2023-07-15 | 2024-01-30 | $85,000.00 | $67,845.36 | 79% | Medium | User Acceptance Testing (Nov 15)
PJ002 | New Data Center Deployment | James Reed | Infrastructure | Planning | 2023-11-01 | 2024-06-30 | $450,000.00 | $78,955.78 | 17% | High | Site Finalization (Dec 12)
PJ003 | Customer Support Automation | Laura Chen | Customer Experience | In Progress | 2023-08-10 | 2024-03-15 | $65,750.00 | $49,683.94 | 75% | Low | System Integration (Nov 22)
PJ004 | Mobile App Redesign | Marcus Taylor | Product Development | On Hold | 2023-09-18 | 2024-05-31 | $135,500.00 | $87,456.12 | 64% | Medium | Design Review (Nov 28)
PJ005 | Digital Marketing Campaign Launch | Nina Patel | Marketing | Completed | 2023-10-01 | 2023-10-31 | $45,875.99 | $44,987.65 | 100% | Low | N/A
Totals: | [6 empty] | $782,125.99 | $338,929.85 | N/A | N/A
Legend:Status - Completed ¦ In Progress ¦ On Hold ¦ Planning. Risk Level - Low, Medium, High.