## Worksheet
Project | Phase | Start Date | End Date | Status | Owner | Budget (USD)
Website Redesign | Planning | 2023-10-01 | 2023-10-15 | In Progress | Jane Smith | 50,000.00
Website Redesign | Design | 2023-10-16 | 2023-11-30 | In Progress | Jane Smith | 75,000.00
Website Redesign | Development | 2023-12-01 | 2024-01-31 | Not Started | Mike Johnson | 150,000.00
Website Redesign | Testing | 2024-02-01 | 2024-02-15 | Not Started | Sarah Lee | 35,000.00
Website Redesign | Launch | 2024-02-16 | 2024-02-28 | Not Started | Jane Smith | 15,000.00
New CRM Implementation | Discovery | 2023-11-01 | 2023-11-30 | In Progress | David Brown | 45,000.00
New CRM Implementation | Design & Build | 2023-12-01 | 2024-03-31 | In Progress | David Brown | 185,000.00
New CRM Implementation | Testing & Training | 2024-04-01 | 2024-05-31 | Not Started | Lisa Wong | 65,000.00
New CRM Implementation | Go Live | 2024-06-01 | 2024-06-15 | Not Started | David Brown | 35,000.00
Data Migration Project | Assessment | 2023-12-15 | 2024-01-31 | In Progress | Raj Patel | 40,000.00
Data Migration Project | Execution | 2024-02-15 | 2024-11-30 | Not Started | Raj Patel | 95,000.00
Data Migration Project | Validation & Closeout | 2024-12-01 | 2024-12-31 | Not Started | Raj Patel | 30,000.00