## Worksheet
Operations Dashboard - Monthly Project Plan (March 2024)
Project ID | Project Name | Owner | Start Date | End Date | Status | Budget (USD) | % Complete | Action Items / Notes
PJ-001 | Website Redesign Initiative | Emma Johnson | 2024-03-01 | 2024-03-31 | In Progress | $55,000 | 68% | Final UI review scheduled for March 15.
PJ-002 | Customer Portal Upgrade | Liam Chen | 2024-03-10 | 2024-03-31 | On Track | $78,500 | 85% | Final testing phase beginning March 22.
PJ-003 | Data Migration Project | Sophia Rodriguez | 2024-03-05 | 2024-03-28 | Delayed (Risk) | $95,300 | 47% | Bottleneck in legacy data cleanup. Requires additional resources.
PJ-004 | Marketing Automation Rollout | Noah Williams | 2024-03-15 | 2024-03-31 | On Track | $42,800 | 96% | Ready for final QA; deployment planned March 31.
PJ-005 | IT Security Audit & Compliance | Ava Thompson | 2024-03-01 | 2024-03-31 | In Progress (High Risk) | $67,950 | 59% | Audit scope expanded; needs executive approval for budget increase.
Total Projects: | [6 empty] | 5 | N/A