## Worksheet
Operations Dashboard - Project Plan
Project ID | Project Name | Start Date | End Date | Status | Progress
PJ001 | Website Redesign Initiative | 2023-06-15 | 2023-11-30 | In Progress
PJ002 | Customer Portal Upgrade | 2023-07-10 | 2024-01-15 | In Progress
PJ003 | Mobile App Development | 2023-08-21 | 2024-05-15 | In Progress
PJ004 | CRM System Integration | 2023-11-01 | 2024-03-31 | Completed
PJ005 | Supply Chain Optimization | 2023-12-15 | 2024-08-31 | Delayed
Task ID | Task Name | Owner | Start Date | Due Date | Status
TASK001-01 | UI/UX Design Phase | Sarah Johnson | 2023-06-15 | 2023-07-31 | Completed
TASK001-02 | Frontend Development | Mark Wilson | 2023-08-15 | 2023-10-31 | In Progress
TASK001-03 | Backend Integration | Lisa Chen | 2023-09-15 | 2023-11-15 | In Progress
TASK002-01 | Requirements Gathering | James Reed | 2023-07-15 | 2023-08-15 | Completed
TASK002-02 | Backend API Development | Rachel Kim | 2023-08-16 | 2023-11-30 | In Progress
TASK003-01 | Wireframing & Prototyping | Alex Turner | 2023-08-21 | 2023-10-15 | Completed
TASK004-01 | System Analysis & Mapping | David Lopez | 2023-11-01 | 2023-12-31 | Completed
TASK005-01 | Process Audit & Assessment | Emma Patel | 2023-12-15 | 2024-01-31 | Delayed
Project | Team Members | Total Hours Allocated | Risk Level | Mitigation Strategy
Website Redesign Initiative | Sarah Johnson, Mark Wilson, Lisa Chen, Tom Baker | 450 hrs | Medium
Customer Portal Upgrade | James Reed, Rachel Kim, Anna Smith, Ben Carter | 670 hrs | High
Mobile App Development | Alex Turner, Emily Davis, Chris Reed, Laura Wu | 890 hrs | High
CRM System Integration | David Lopez, Maria Gonzales, Peter Liu | 315 hrs | Low
Supply Chain Optimization | Emma Patel, Robert White, Sophia Liu, James Brown | 240 hrs | Critical