## Worksheet
Operations Dashboard - Project Template (Detailed)
Project ID | Project Name | Department | Status | Budget ($) | Actual Cost ($) | Progress (%) | Scheduled Start Date | Scheduled End Date | Actual End Date | Risk Level
PJ001 | Infrastructure Upgrade Project | IT Operations | Completed | 500,000.00 | 485,231.45 | 100% | 2023-12-15 | 2024-03-31 | 2024-03-25 | Low
PJ002 | Data Migration Initiative | Data Services | In Progress | 350,000.00 | 298,147.32 | 85% | 2024-01-15 | 2024-11-30 | - | Medium
PJ003 | Customer Portal Redesign | Product Development | In Progress | 420,000.00 | 315,678.91 | 75% | 2024-02-15 | 2024-12-31 | - | High
PJ004 | Security Compliance Audit | Compliance & Security | Delayed | 120,000.00 | 95,432.67 | 45% | 2024-01-31 | 2024-11-30 | - (Expected: 2025-01-31) | High
PJ005 | Cloud Migration Phase 2 | IT Operations | In Progress | 650,000.00 | 421,893.75 | 65% | 2024-11-30 | 2025-12-31 | - | Medium
Total Projects: 5 ¦ Active: 4 ¦ Completed: 1 ¦ Delayed: 1 |  |  |  | $2,040,000.00 | $1,516,384.79 | 72%
Overall Budget Utilization: 74.3% | [5 empty] | Average Risk Level: Medium
Last updated on May 15, 2024 ¦ Generated from Operations Management System