## Worksheet
Operations Dashboard - Quarterly Project Template
Project ID | Project Name | Quarter | Planned Start Date | Planned End Date | Status (Target) | Status (Actual) | Budget (Planned) | Budget (Actual) | Action Items
Q1 - January 2024 - March 2024
PROJ-001 | System Migration Phase I | Q1 2024 | Jan 5, 2024 | Mar 15, 2024 | On Track (Target) | On Track (Actual) | $150,000 | $148,500 | Review migration logs weekly
PROJ-002 | CRM Integration Upgrade | Q1 2024 | Jan 10, 2024 | Mar 31, 2024 | On Track (Target) | Delayed (Actual) | $95,000 | $102,400 | Address API compatibility issues by Feb 15
Q2 - April 2024 - June 2024
PROJ-003 | Security Compliance Audit | Q2 2024 | Apr 1, 2024 | Jun 15, 2024 | On Track (Target) | On Track (Actual) | $75,000 | $73,650 | Finalize audit report by June 18
Q3 - July 2024 - September 2024
PROJ-004 | User Experience Redesign | Q3 2024 | Jul 1, 2024 | Sep 30, 2024 | On Track (Target) | On Track (Actual) | $180,000 | $175,300 | Conduct user testing in week 8 and 12
Q4 - October 2024 - December 2024
PROJ-005 | Global Deployment Rollout | Q4 2024 | Oct 1, 2024 | Dec 31, 2024 | On Track (Target) | On Track (Actual) | $450,000 | $445,750 | Coordinate with regional teams monthly
Total Projects |  | 5 | [6 empty] | $945,000 | $945,600
Prepared on January 5, 2024 ¦ Operations Dashboard - Quarterly Project Template v1.0