## Worksheet
Project Name | Phase | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | % Complete
Website Redesign Project | Design Phase | 2024-01-15 | 2024-03-31 | 2024-01-15 | -- | On Track | 65%
CRM Migration | Implementation Phase | 2024-02-01 | 2024-05-31 | 2024-03-15 | -- | Delayed | 38%
Cloud Infrastructure Upgrade | Testing Phase | 2024-04-15 | 2024-06-30 | 2024-05-15 | -- | On Track | 78%
Mobile App Development | Development Phase | 2024-01-10 | 2024-10-31 | 2024-03-18 | -- | On Track | 57%
Total Projects: | [5 empty] | 4 | 57%