## Worksheet
Operations Dashboard
Advanced Project Timeline Overview (Q3 2024)
Project ID | Project Name | Task/Phase | Start Date | End Date | Status | Progress (%)
P001 | Cloud Infrastructure Upgrade | Phase 1: Assessment & Planning | 2024-07-01 | 2024-07-15 | In Progress
|  | Phase 2: Server Migration | 2024-07-16 | 2024-08-31 | Pending
|  | Milestone: Cutover Complete | 2024-09-15 | Overdue | Overdue
P002 | Customer Portal Redesign | UI/UX Design Phase | 2024-06-15 | Completed | Completed
|  | Front-End Development | 2024-08-15 | In Progress | In Progress
P003 | Supply Chain Analytics Tool | Data Pipeline Setup | 2024-05-15 | Completed | Completed
|  | Dashboard Development | 2024-07-15 | In Progress | In Progress
|  | Milestone: Pilot Launch | Pending | Pending | Pending
Overall Project Status: |  |  |  |  | 68% On Track