## Worksheet
Project | Phase | Start Date | End Date | Status | % Complete
Website Redesign | Planning & Design | 2024-03-01 | 2024-03-15 | Completed | 100%
Website Redesign | Development | 2024-03-16 | 2024-04-15 | Ongoing | 75%
Website Redesign | Testing & QA | 2024-04-16 | 2024-05-15 | Delayed | 30%
CRM Integration | Requirements Gathering | 2024-02-15 | 2024-03-15 | Completed | 100%
CRM Integration | System Design | 2024-03-16 | 2024-04-15 | Completed | 100%
CRM Integration | Implementation | 2024-04-16 | 2024-05-31 | Ongoing | 65%
Data Migration | Assessment & Planning | 2024-03-01 | 2024-03-31 | Completed | 100%
Data Migration | Execution & Validation | 2024-04-01 | 2024-05-31 | Delayed | 55%