## Worksheet
Operations Dashboard
Project Timeline - Detailed View
Project ID | Project Name | Start Date | End Date | Status | Progress (%) | Budget (USD)(Allocated/Spent)(% Used)
PROJ-001 | Enterprise Resource Planning System Upgrade | 2024-01-15 | 2024-06-30 | Active | 68% | $500,000/ $340,250 (68%)
PROJ-012 | Customer Portal Redesign | 2024-02-10 | 2024-08-15 | Active | 52% | $320,000/ $166,400 (52%)
PROJ-034 | Global Data Center Expansion | 2023-11-01 | 2024-10-31 | Active | 76% | $2,800,000/ $2,128,000 (76%)
PROJ-145 | AI-Powered Analytics Integration | 2024-03-25 | 2025-01-31 | Active | 41% | $650,000/ $266,500 (41%)
PROJ-237 | Supply Chain Digitalization Initiative | 2023-10-15 | 2024-12-31 | Completed | 100% | $425,000/ $423,759 (99.7%)
PROJ-568 | Remote Work Infrastructure Upgrade | 2024-01-05 | 2024-09-30 | Delayed (Planned) | 48% | $175,000/ $84,325 (48.2%)
Legend:
•Completed: Project finished successfully
•Active: On track with current progress