## Worksheet
Operations Dashboard - Project Timeline (Extended)
Project ID | Project Name | Milestone Schedule |  |  |  |  | Status | Progress (%) | Owner
|  | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Duration (Days)
PJ001 | Website Redesign Phase 1 | 2024-03-05 | 2024-03-15 | 2024-04-15 | -- | 65
PJ002 | Mobile App Launch v2.0 | 2024-03-18 | 2024-03-18 | 2024-11-30 | -- | 95
PJ003 | Data Center Migration (Phase A) | 2024-04-15 | -- | 2024-12-15 | -- | 36
PJ004 | Cybersecurity Audit & Compliance Review | 2024-05-15 | 2024-06-15 | 2024-11-30 | 2024-11-30 | 78
PJ005 | HR Onboarding System Integration | 2024-03-10 | 2024-03-17 | 2024-11-35 | -- | 56
Total Projects: | [6 empty] | 5 | 62%
Key Indicators: 3 In Progress ¦ 1 Completed ¦ 1 Delayed ¦ 4 On Track (≥60%)