## Worksheet
Operations Dashboard
Project Timeline - Financial View
Project Name | Phase | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Budget Variance (USD)
Site Construction - Phase I | Design & Permitting | 2024-01-15 | 2024-03-31 | Ongoing | $850,000 | $678,921 | $171,079
Site Construction - Phase I | Foundation & Site Prep | 2024-04-01 | 2024-06-30 | Ongoing | $1,575,890 | $1,492,347 | $83,543
IT Infrastructure Upgrade | System Assessment | 2024-02-01 | 2024-04-15 | Completed | $389,500 | $367,489 | $22,011
IT Infrastructure Upgrade | Hardware Deployment | 2024-05-01 | 2024-10-31 | Delayed | $876,435 | $692,756 | $183,679
Marketing Campaign - Q2 | Strategy & Creative Development | 2024-04-15 | 2024-06-15 | Completed | $198,750 | $192,387 | $6,363
Marketing Campaign - Q2 | Campaign Execution & Analytics | 2024-07-01 | 2024-09-30 | Completed | $556,891 | $563,412 | $6,521
Product Launch - New Line X | Prototype Development | 2024-03-01 | 2024-06-30 | Completed | $789,456 | $758,923 | $30,533
Product Launch - New Line X | Manufacturing & QA Testing | 2024-07-15 | 2024-11-30 | Ongoing | $3,456,789 | $2,890,178 | $566,611
Supply Chain Optimization | Data Analysis & Process Mapping | 2024-01-20 | 2024-05-31 | Completed | $678,934 | $657,891 | $21,043
Supply Chain Optimization | Supplier Re-negotiation & Implementation | 2024-06-15 | 2024-12-31 | Delayed | $987,654 | $783,456 | $204,198
Total Project Costs (All Phases) |  |  |  | 10 Projects | $10,285,495 | $9,617,384 | $668,111
Last updated:April 5, 2024¦ Data source: ERP & Project Management Systems