## Worksheet
Operations Dashboard - Project Timeline (Multi-Page)
Project ID | Project Name | Start Date | Target End Date | Status | Progress (%) | Budget (USD)
P001 | Website Redesign Phase 1 | 2024-03-15 | 2024-06-30 | In Progress | 65% | $85,000
P002 | Cloud Migration Initiative | 2024-01-10 | 2024-11-30 | In Progress | 85% | $375,000
P003 | Customer Portal Development | 2024-04-12 | 2024-11-15 | In Progress | 78% | $95,000
P004 | Internal CRM Upgrade | 2023-11-28 | 2024-12-31 | Completed | 100% | $65,000
P005 | Data Analytics Platform Launch | 2024-12-17 | 2025-10-31 | In Progress | 45% | $280,000
Project ID | Phase | Start Date | End Date | Status | Description
P001 | Requirements Gathering | 2024-03-15 | 2024-04-30 | Completed | Gathered stakeholder input and finalized requirements.
P001 | UI/UX Design | 2024-05-01 | 2024-06-15 | In Progress | Design mockups and user flow prototypes.
P001 | Front-End Development | 2024-06-16 | 2024-8-31 | In Progress | Implement responsive front-end components.
P002 | Assessment & Planning | 2024-01-15 | 2024-3-31 | Completed | Analyzed current infrastructure and developed migration strategy.
P002 | Database Migration | 2024-4-15 | 2024-7-31 | In Progress | Migrated on-premise databases to cloud environment.
P003 | Architecture Design | 2024-04-15 | 2024-5-15 | Completed | Fully designed microservices architecture and API contracts.
P004 | Upgrade Implementation | 2023-11-30 | 2024-6-30 | Completed | Successfully migrated to latest CRM version.
P005 | Data Pipeline Setup | 2024-12-17 | 2025-3-31 | In Progress | Configured ETL processes and data ingestion pipelines.
Project ID | Team Member | Role | Hrs/Week | Status
P001 | Alice Johnson | Lead UX Designer | 25 | Active
P002 | Robert Chen | Cloud Architect | 35 | Active
P003 | Maya Rodriguez | Backend Developer | 28 | Active
P005 | James Wilson | Data Engineer | 32 | Active