## Worksheet
Operations Dashboard - Project Timeline
Project ID | Project Name | Description | Start Date | End Date | Status | Progress (%)
PJ001 | Website Redesign | Complete overhaul of company website with new UI/UX and CMS integration. | 2024-04-15 | 2024-06-30 | In Progress | 65%
PJ002 | Cloud Migration | Migrate all internal systems to AWS cloud infrastructure.2024-05-10 | 2024-11-30 | In Progress | 45%
PJ003 | Mobile App Development - Phase 1 Build MVP for iOS and Android with core features.2024-03-25 | 2024-07-15 | Pending | 18%
PJ004 | CRM System Upgrade Enhance customer management features and integrate with marketing tools.2024-06-15 | 2024-10-31 | In Progress | 37%
PJ005 | Internal Training Program Launch Roll out new onboarding and skill development curriculum.2024-07-15 | 2024-12-31 | Pending | 5%
Total Projects:5 ¦Active:4 ¦Completed:1
Last Updated: April 5, 2024