## Worksheet
Operations Dashboard
Project Timeline (Planning View)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
PRJ-001 | Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | Completed
PRJ-002 | Requirements Gathering | 2024-03-16 | 2024-03-31 | 16 | In Progress
PRJ-003 | Design Phase | 2024-04-01 | 2024-04-15 | 15 | In Progress
PRJ-004 | Development - Core Modules | 2024-04-16 | 2024-05-31 | 46 | In Progress
PRJ-005 | Testing & QA | 2024-06-01 | 2024-06-30 | 30 | Delayed
PRJ-006 | User Training & Documentation | 2024-07-01 | 2024-07-15 | 15 | In Progress
PRJ-007 | Deployment & Go-Live | 2024-07-16 | 2024-07-31 | 16 | Delayed
Milestone: Project Completion (Target Date: 2024-07-31)