## Worksheet
Operations Dashboard - Quarterly Project Timeline
Project Name | Owner | Quarterly Milestones
|  | Q1 (Jan - Mar) | Q2 (Apr - Jun) | Q3 (Jul - Sep) | Q4 (Oct - Dec)
Website Redesign | Jane Smith | Initiation, Planning, Design Approval | Front-end Development | Testing & Feedback Integration | Landing Page Launch & Reporting
Q1 Summary: Jan - Mar 2024
Product Launch - Phase 1 | Mark Johnson | Market Research, MVP Design | Sprint Planning & Dev Setup | User Testing (Beta) | Limited Release & Feedback Collection
Q2 Summary: Apr - Jun 2024
CRM Integration Upgrade | Emily Chen | Requirements Gathering | Data Mapping, System Testing | User Training Sessions Prep | Full Rollout & Monitoring Phase I
Q3 Summary: Jul - Sep 2024
AI-Powered Analytics Module | David Kim | Data Pipeline Setup | Model Training & Validation | Dashboard Development (Internal) | Pilot Launch with Key Clients
Q4 Summary: Oct - Dec 2024
Global Expansion Initiative | Lisa Rodriguez | Market Analysis & Legal Review | Partner Selection & Contract Finalization | Pilot Office Setup (Region A) | Full Regional Launch & KPI Review
*All dates and milestones are subject to change based on resource availability and stakeholder feedback.