## Worksheet
Operations Dashboard - Project Timeline
Team Use ¦ Last Updated: April 5, 2024 ¦ Version: 2.1
Project ID | Project Name | Lead Team Member | Start Date | Planned End Date | Actual End Date | Status
PJ001 | E-commerce Platform Upgrade | Sarah Johnson | 2024-01-15 | 2024-05-30 | --:--:-- | Ongoing
PJ002 | CRM Integration Phase 1 | Mike Chen | 2024-02-01 | 2024-03-15 | 2024-03-14 | Completed
PJ003 | Mobile App Redesign | Laura Martinez | 2024-01-20 | 2024-06-15 | --:--:-- | Delayed (Pending Approval)
PJ004 | Cloud Migration Initiative | Daniel Kim | 2024-03-10 | 2024-11-30 | --:--:-- | Ongoing (Phase 2)
PJ005 | Internal Training Portal Launch | Emily Parker | 2024-01-30 | 2024-04-15 | 2024-04-15 | Completed