## Worksheet
Operations Dashboard
Project Timeline - Tracking View
Project ID | Project Name | Phase / Task | Start Date | End Date | Status | % Complete
Project Alpha - Website Redesign (Q2 2024)
PA-001 | Website Redesign | Requirement Gathering | Mar 1, 2024 | Mar 15, 2024 | Completed
PA-002 | Website Redesign | UI/UX Design | Mar 16, 2024 | Apr 5, 2024 | In Progress
PA-003 | Website Redesign | Frontend Development | Apr 6, 2024 | May 15, 2024 | In Progress
Project Beta - Mobile App Launch (Q3 2024)
PB-001 | Mobile App Development | App Architecture Planning | Apr 1, 2024 | Apr 15, 2024 | Completed
PB-002 | Mobile App Development | Core Feature Implementation | Apr 16, 2024 | Jun 30, 2024 | In Progress
Project Gamma - CRM Integration (Q4 2024)
PG-001 | CRM Integration | Data Migration Planning | Jun 1, 2024 | Jun 15, 2024 | Delayed
PG-002 | CRM Integration | API Development & Testing | Jun 16, 2024 | Aug 31, 2024 | In Progress
Total Tasks: | [5 empty] | 10