## Worksheet
Operations Dashboard - Project Tracker (Detailed)
Project ID | Project Name | Description | Start Date | End Date | Status | Priority | Budget (USD) | Actual Cost (USD) | Progress (%) | Assigned Team | Last Updated
P001 | Cloud Migration Initiative | Migrate all on-premise servers to AWS cloud environment. | 2024-01-15 | 2024-06-30 | In Progress | High | $85,000.00 | $47,235.50 | 56% | DevOps Team A | 2024-11-18
P002 | Customer Portal Redesign | Complete UI/UX overhaul of the client-facing portal. | 2024-03-10 | 2024-11-30 | Pending | High | $65,500.00 | $8,742.35 | 13% | UX/UI Design Team | 2024-11-17
P003 | Inventory Management System Upgrade | Implement real-time inventory tracking and forecasting. | 2024-05-25 | 2024-11-15 | Completed | Medium | $78,300.00 | $75,986.42 | 100% | IT Infrastructure Team | 2024-11-15
P004 | Cybersecurity Enhancement Program | Implement multi-factor authentication and threat detection. | 2024-02-18 | 2025-01-31 | In Progress | High | $95,750.00 | $48,693.87 | 42% | Cybersecurity Task Force | 2024-11-18
P005 | HR Onboarding Platform Launch | Develop digital onboarding workflow for new employees. | 2024-11-01 | 2025-03-31 | Pending | Medium | $58,900.00 | $4,123.98 | 7% | HR Technology Team | 2024-11-16
P006 | Data Analytics Dashboard Revamp | Enhance reporting tools with interactive visualizations. | 2024-11-15 | 2025-04-30 | In Progress | High | $68,400.00 | $19,567.21 | 28% | Data Science Team | 2024-11-18
P007 | Mobile App Performance Optimization | Improve load time and reduce crashes by 45%. | 2024-12-15 | 2025-03-15 | Delayed | Medium | $49,700.00 | $13,896.45 | 22% | Mobile Development Team | 2024-11-17
P008 | Customer Feedback Integration System | Integrate NPS and survey tools into CRM platform. | 2024-11-25 | 2025-05-31 | Pending | Low | $38,600.00 | $1,498.76 | 3% | Product Management Team | 2024-11-15
P009 | Supply Chain Visibility Project | Build real-time shipment tracking across vendors. | 2024-11-30 | 2025-10-31 | Pending | High | $87,500.00 | $9,432.67 | 8% | Logistics & IT Team | 2024-11-16
P010 | Internal Training Portal Rollout | Launch e-learning platform for employee development. | 2025-01-15 | 2025-08-31 | Pending | Medium | $64,300.00 | $1,879.14 | 2% | HR & IT Team | 2024-11-15