## Worksheet
Operations Dashboard
Project Tracker - Manager View
Project Name | Owner | Status | Progress (%) | Start Date | Due Date | Budget ($)(Actual/Planned)(Cost Variance) | Priority
Website Redesign Initiative | Sarah Johnson | Ongoing | 75% | 2023-09-15 | 2024-01-31 | $89,456 / $95,000 (–$5,544) | High
Mobile App Launch | James Wilson | Ongoing | 60% | 2023-11-01 | 2024-03-15 | $234,789 / $250,000 (–$15,211) | High
CRM Integration Upgrade | Lisa Chen | Delayed | 45% | 2023-08-10 | 2023-11-30 | $67,945 / $65,000 (+$2,945) | Medium
Customer Onboarding Portal | Michael Brown | Completed | 100% | 2023-12-05 | 2024-01-15 | $43,896 / $45,000 (–$1,104) | Medium
Supply Chain Optimization | Amanda Reed | Ongoing | 80% | 2023-10-22 | 2024-06-30 | $156,789 / $165,000 (–$8,211) | High
Employee Training Program | David Lee | Ongoing | 35% | 2024-01-10 | 2024-12-31 | $78,945 / $85,000 (–$6,055) | Low