## Worksheet
Monthly Project Tracker
Project Name | Department | Start Date | Target End Date | Status | % Complete | Budget (USD)
Website Redesign Initiative | Marketing | 2024-03-15 | 2024-05-15 | In Progress | 78% | $45,000
CRM Integration Project | IT & Operations | 2024-02-10 | 2024-06-30 | In Progress | 55% | $89,500
Employee Training Program | HR | 2024-03-21 | 2024-04-30 | Completed | 100% | $18,750
Inventory Automation System | Logistics | 2024-03-18 | 2024-07-15 | In Progress | 63% | $145,900
Customer Feedback Portal Launch | Product Development | 2024-03-05 | 2024-04-15 | Delayed | 47% | $38,600
Total Projects:5¦ In Progress:3¦ Completed:1¦ Delayed:1