## Worksheet
Weekly Project Tracker - Operations Dashboard
Project ID | Project Name | Team Lead | Status | Start Date | Expected End Date | Progress (%) | Milestone Achieved (This Week)
PJ001 | Website Redesign Initiative | Jane Smith | In Progress | 2023-10-15 | 2024-01-31 | 65% | UI/UX Mockups Finalized & Approved
PJ002 | Cloud Migration Phase 1 | Robert Johnson | In Progress | 2023-11-01 | 2024-03-31 | 45% | Data Migration Script Completed & Tested
PJ003 | CRM System Upgrade | Emily Davis | Completed | 2023-10-01 | 2023-12-31 | 100% | All Modules Upgraded and User Training Completed
PJ004 | Mobile App Development (v2.0) | Michael Brown | Delayed | 2023-11-15 | 2024-06-30 | 35% | Firebase Integration Delayed Due to API Issues
PJ005 | Security Compliance Audit | Sarah Wilson | In Progress | 2023-12-01 | 2024-03-31 | 58% | Risk Assessment Report Drafted and Reviewed
Last Updated:October 26, 2023¦ Weekly Report (Week of October 15 - October 21, 2023)