## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority
T001 | Project Kickoff Meeting | Alice Johnson | 2023-10-05 | 2023-10-05 | Completed | High
T002 | Resource Allocation Plan | Bob Smith | 2023-10-06 | 2023-10-10 | In Progress | High
T003 | System Design Review | Carol Lee | 2023-10-11 | 2023-10-15 | Pending Approval | Moderate
T004 | Development Sprint 1 | Dan Brown | 2023-10-16 | 2023-10-27 | Scheduled | High
T005 | QA Testing Phase 1 | Eva Garcia | 2023-10-28 | 2023-11-03 | Scheduled | Moderate
T006 | User Acceptance Testing (UAT) | Frank Miller | 2023-11-04 | 2023-11-15 | Scheduled | High