## Worksheet
Task ID | Task Name | Assignee | Start Date | End Date | Status | Priority
T001 | Project Kickoff | Sarah Johnson | 2024-01-15 | 2024-01-17 | Completed | High
T002 | Requirements Gathering | Michael Chen | 2024-01-18 | 2024-01-31 | In Progress | Medium
T003 | System Design Phase | Lisa Rodriguez | 2024-02-01 | 2024-02-15 | Pending | High
T004 | Development Sprint 1 | James Wilson | 2024-02-16 | 2024-03-01 | In Progress | Medium
T005 | User Acceptance Testing | Emma Taylor | 2024-03-02 | 2024-03-15 | Not Started | High
T006 | Deployment Preparation | David Kim | 2024-03-16 | 2024-03-25 | Not Started | Medium
T007 | Final Review & Sign-off | Olivia Martinez | 2024-03-26 | 2024-03-31 | Not Started | High