## Worksheet
Operations Dashboard - Schedule Planner (Client View)
Task ID | Task Name | Description | Assigned To | Start Date | End Date | Status
T001 | Project Kickoff Meeting | Initial planning session with client and internal team. | Jane Smith (Client Rep) | 2024-05-15 | 2024-05-17 | Completed
T002 | Requirements Gathering | Collect detailed business requirements. | Mike Johnson (Project Manager) | 2024-05-18 | 2024-05-29 | In Progress
T003 | Design Phase - Wireframes | Create initial UI wireframes. | Alice Brown (UI Designer) | 2024-05-30 | 2024-06-15 | Pending
T004 | Development Sprint 1 | Frontend implementation of core features. | Team A (Dev) | 2024-06-16 | 2024-07-05 | Pending
T005 | UAT Preparation | Set up test environment and documentation. | Sarah Lee (QA Lead) | 2024-07-16 | 2024-07-31 | Pending
T006 | Client Feedback Session | Present UI/UX for client review. | Jane Smith (Client Rep) | 2024-07-18 | 2024-07-19 | Pending
T007 | Final Deployment | Deploy final version to production. | DevOps Team (Deployment) | 2024-08-15 | 2024-08-31 | Pending