## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority
001 | Project Kickoff Meeting | John Smith | 2023-10-05 | 2023-10-05 | In Progress | High
002 | Requirement Gathering | Sarah Johnson | 2023-10-06 | 2023-10-15 | Not Started
003 | System Design Phase | Mike Brown | 2023-10-16 | In Progress (50%)
004 | Development Sprint 1 | Lisa White | 2023-10-18 to 2023-11-05
005 | UI/UX Review Session | David Lee | Scheduled for 2023-11-10
006 | QA Testing Phase | Anna Garcia | Not Started - Planned for 2023-11-15
007 | Deployment Preparation | Robert Taylor | Scheduled for 2023-11-30
008 | Final Project Review | John Smith | Scheduled for 2023-12-15