## Worksheet
Operations Dashboard - Schedule Planner
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority
#001 | Project Kickoff Meeting | Alice Johnson | 2024-04-05 | 2024-04-05 | Complete | High
#002 | Requirements Gathering | Bob Smith | 2024-04-06 | 2024-04-15 | Pending | High
#003 | Design Phase Approval | Charlie Brown | 2024-04-16 | 2024-04-25 | Pending | Medium
#004 | Development Sprint 1 | Diana Lee | 2024-04-26 | 2024-05-17 | Pending | High
#005 | User Testing Session | Edward Reed | 2024-05-18 | 2024-06-19 | Delayed | Medium
#006 | Final Deployment & Handover | Fiona Green | 2024-06-20 | 2024-07-15 | Pending | High
Template for Personal Use ¦ Operations Dashboard - Schedule Planner