## Worksheet
Task | Assigned To | Start Date | End Date | Status
Project Kickoff Meeting | Jane Smith | 2023-10-05 | 2023-10-05 | Completed
Data Collection Phase | John Doe | 2023-10-06 | 2023-10-15 | In Progress
Design Review Session | Alice Johnson | 2023-10-16 | 2023-10-17 | Scheduled
Development Sprint 1 | Team A | 2023-10-18 | 2023-10-30 | Scheduled
Testing & QA | QA Team | 2023-10-31 | 2023-11-10 | Pending
Final Deployment | DevOps Team | 2023-11-13 | 2023-11-15 | Pending
Total Tasks | 6