## Worksheet
Operations Dashboard
Schedule Planner - Startup Style
Task ID | Task Name | Team Member | Start Date | End Date | Status | Action Required(Priority)
TASK-001 | Project Kickoff Meeting | Alice Johnson | 2025-04-05 | 2025-04-05 | Completed | ReviewHigh
TASK-002 | Design Wireframes (V1) | Mike Chen | 2025-04-06 | 2025-04-13 | Active | EditHigh
TASK-003 | Frontend Development Sprint 1 | Sarah Lee | 2025-04-14 | 2025-04-28 | Pending | AssignMedium
TASK-004 | API Integration Testing | Daniel Park | 2025-04-17 | 2025-04-25 | Active | MonitorHigh
TASK-005 | User Acceptance Testing (UAT) | Linda Torres | 2025-04-30 | 2025-05-14 | Pending | PrepareHigh
TASK-006 | Deploy to Production (v1.0) | Ryan Clark | 2025-05-15 | 2025-05-16 | Pending | ScheduleUrgent