## Worksheet
Operations Dashboard - Schedule Planner (Tracking View)
Task ID | Task Name | Description | Assigned To | Start Date | End Date | Status
T001 | System Upgrade Prep | Prepare infrastructure for system upgrade | Alice Johnson | 2023-10-23 | 2023-11-05 | In Progress
T002 | Data Migration Phase 1 | Migrate user database to new platform | Carlos Mendez | 2023-11-06 | 2023-11-15 | Pending
T003 | Security Audit Review | Conduct comprehensive security assessment | Sarah Lin | 2023-11-16 | 2023-11-25 | Pending
T004 | Client Onboarding Training | Train client teams on new system features | James Reed | 2023-11-26 | 2023-12-05 | Pending
T005 | Final Testing & QA | Execute final validation tests before release | Linda Wu | 2023-12-18 | 2023-12-30 | Delayed
T006 | Go-Live Deployment | Full system rollout and cutover event | Robert Kim | 2023-12-31 | 2024-01-05 | Pending
Last Updated: October 24, 2023 ¦ Total Tasks: 6 ¦ In Progress: 1 ¦ Completed: 0