## Worksheet
Task ID | Task Name | Assignee | Start Date | Due Date | Status | Priority
T001 | Project Kickoff Meeting | Jane Doe | 2023-10-05 | 2023-10-15 | In Progress | High
T002 | Requirements Gathering | John Smith | 2023-10-16 | 2023-11-05 | In Progress | High
T003 | UI/UX Design Phase 1 | Alice Johnson | 2023-11-06 | 2023-11-30 | In Progress | Medium
T004 | Backend Development Setup | Robert Brown | 2023-11-15 | 2023-12-15 | Overdue | High
T005 | Database Schema Design | Sarah Wilson | 2023-11-20 | 2023-12-18 | Completed | Medium
T006 | Frontend Component Development | Lisa Garcia | 2023-12-15 | 2024-01-15 | In Progress | High
Total Tasks:6 ¦In Progress:3 ¦Completed:1 ¦Overdue:1