## Worksheet
Operations Dashboard
Project | Task Name | Start Date | End Date | Planned Hours | Actual Hours | Status
Q3 Marketing Campaign
Q3 Marketing Campaign | Market Research & Analysis | 2024-07-01 | 2024-07-15 | 60 | 58
Q3 Marketing Campaign | Creative Design Development | 2024-07-16 | 2024-07-31 | 85 | 89
Q3 Marketing Campaign | Content Creation & Copywriting | 2024-08-01 | 2024-08-15 | 75 | -
Q3 Marketing Campaign | Campaign Launch & Monitoring | 2024-08-16 | 2024-09-15 | 95 | -
Product Development Sprint 4.1
Product Development Sprint 4.1 | Backend API Enhancement | 2024-07-05 | 2024-07-31 | 68 | 68
Product Development Sprint 4.1 | Frontend UI/UX Optimization | 2024-08-01 | 2024-08-31 | 96 | -
Product Development Sprint 4.1 | QA Testing & Bug Fixing | 2024-09-01 | 2024-09-15 | 78 | -
Customer Support Revamp Initiative
Customer Support Revamp Initiative | Process Audit & Review | 2024-07-10 | 2024-07-31 | 55 | 61
Customer Support Revamp Initiative | Ticketing System Upgrade Planning | 2024-08-01 | 2024-08-31 | 59 | -
Customer Support Revamp Initiative | Training Program Development | 2024-09-01 | 2024-10-15 | 67 | -In Progress
Total Planned Hours: |  |  |  | 762 | 315