## Worksheet
Operations Dashboard - Quarterly Weekly Planner
Week | Key Metrics & Targets
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Week 1 (Jan 1–7) | Weekly Objective: Initiate Q1 operational setup and team onboarding
| Task | Status | Owner | Target KPIs
| Team Kickoff Meeting (Mon) | In Progress | John Doe | 100% attendance, action items documented
Week 2 (Jan 8–14) | Weekly Objective: Launch new process workflow and training modules
| Task | Status | Owner | Target KPIs
| Process Flow Design (Tue) | Completed | Sarah Lee | Approved by operations lead
Week 3 (Jan 15–21) | Weekly Objective: Conduct team training and feedback collection
| Task | Status | Owner | Target KPIs
| Training Session I (Wed) | Completed | Mike Chen | 95% attendance, 4.6/5 avg rating
Week 4 (Jan 22–28) | Weekly Objective: Evaluate training effectiveness and optimize workflow
| Task | Status | Owner | Target KPIs
| Post-Training Survey (Thu) | Completed | Emma Wilson | 90% response rate, action items identified
Week 5 (Jan 29 – Feb 4) | Weekly Objective: Implement feedback into operational protocols
| Task | Status | Owner | Target KPIs
| Protocol Update Finalization (Mon) | In Progress | Alex Brown | 60% completed, review scheduled Friday
Week 6 (Feb 5–11) | Weekly Objective: Pilot revised workflow with selected departments
| Task | Status | Owner | Target KPIs
| Pilot Launch (Wed) | Pending | David Kim | Launch scheduled for Wed, Feb 7
Week 7 (Feb 12–18) | Weekly Objective: Monitor pilot performance and collect real-time data
| Task | Status | Owner | Target KPIs
| Daily Performance Check (Mon–Fri) | In Progress | Team Leads | Real-time logs updated daily
Week 8 (Feb 19–25) | Weekly Objective: Conduct pilot review and refine implementation plan
| Task | Status | Owner | Target KPIs
| Pilot Review Meeting (Thu) | Pending | Grace Patel | Agenda drafted, invite sent to all stakeholders
Week 9 (Feb 26 – Mar 3) | Weekly Objective: Finalize revised workflow and prepare for full rollout
| Task | Status | Owner | Target KPIs
| Rollout Readiness Check (Fri) | Pending | Robert Green | Final audit due by March 4
Week 10 (Mar 4–10) | Weekly Objective: Initiate full departmental rollout and monitor adoption
| Task | Status | Owner | Target KPIs
| Rollout Start (Mon) | In Progress | Team Leads | Initial feedback received from 8/12 teams
Week 11 (Mar 11–17) | Weekly Objective: Track adoption metrics and resolve issues
| Task | Status | Owner | Target KPIs
| Daily Support Log Update (Tue) | In Progress | Support Team | Issues logged and categorized daily
Week 12 (Mar 18–24) | Weekly Objective: Finalize Q1 review and prepare for Q2 planning
| Task | Status | Owner | Target KPIs
| Q1 Performance Summary (Wed) | Pending | Julia Foster | Data collection in progress, final report due Mar 25
📌 Quarterly Summary: 10 of 12 weeks completed successfully. Final review scheduled for March 25, 2024.